## Test summary report
Tester | NDTKim, NTMDuy, VMLam
Date | 2021-01-15
|  | Number of functions be tested: | 4
|  | Number of test cases: | 20
|  | Number of pass test cases: | 13
|  | Number of fail test case: | 7

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Unable to log in with valid phone number and password | 1. Enter valid phone number '1213123' 2. Enter valid password '123' 3. Click "Đăng nhập" button Expected: Log in successfully Result: Nothing shows | UC01 | High | NDTKim | 2021-01-15 | Open
B002 | App crash when input blank amount | 1. Enter amount ' ' 2. Checkbox 'Đóng góp ẩn danh' 3. Choose payment 'Thẻ ngân hàng' 4. Enter card number ' ' 5. Press 'Đóng góp ngay' button" Expected: Shows prompt Result: App crashes | UC02 | High | NTMDuy | 2021-01-15 | Open
B003 | Negative amount cause total donation to decrease | 1. Enter amount '-100000' 2. Checkbox 'Đóng góp ẩn danh' 3. Choose payment 'Thẻ ngân hàng' 4. Enter card number ' ' 5. Press 'Đóng góp ngay' button Expected: Shows prompt Result: Event donation get subtracted by donation amount | UC02 | High | VMLam | 2021-01-15 | Open
B004 | Create event page cannot be scrolled | Create new fundraising event with overflow data cause distorted UI | UC03 | Medium | VMLam | 2021-01-15 | Open
B005 | Choose wrong date in create event still create event | 1. Fill in page 1 with event name " " ; amount money '1234567 ' and choose category 2. Choose date '11/1/2021' 3. Press 'Tiếp tục' button 4. FIll in page 2 and choose bank 5. Press 'Tiếp tục'button 6. Press checkbox 6. Press 'Hoàn tất' button Expected: shows prompt to refill information Result: sucessfuly create event with negative days count | UC03 | High | NDTKim | 2021-01-15 | Open
B006 | Donation is count but does not update donate log | User makes sucessful donation but is not shown on donation log | UC03 | Medium | NDTKim | 2021-01-15 | Open